## Team
TeamID | Name | Role | RateID | Availability
1 | Alice | Lead | R1 | 1
2 | Bob | Developer | R2 | 0.8
3 | Carol | Developer | R2 | 1
4 | Dave | Designer | R3 | 0.5
5 | Eve | QA | R4 | 1
6 | Frank | Developer | R2 | 0.6
7 | Grace | DevOps | R5 | 0.4
8 | Hank | Manager | R6 | 0.3
Team Size
Total FTE
Avg Availability
Developers

## Rates
RateID | Role | Daily Rate | Overhead % | Loaded Rate
R1 | Lead | 650 | 0.35
R2 | Developer | 500 | 0.3
R3 | Designer | 450 | 0.25
R4 | QA | 400 | 0.28
R5 | DevOps | 550 | 0.32
R6 | Manager | 700 | 0.4
Avg Daily Rate
Avg Loaded Rate
Max Loaded Rate

## Tasks
TaskID | Task Name | Assigned (TeamID) | Days | Daily Rate (looked up) | Effective Days | Task Cost | Phase
T01 | Architecture Design | 1 | 10 |  |  |  | Planning
T02 | UI Mockups | 4 | 8 |  |  |  | Planning
T03 | Backend Core | 2 | 25 |  |  |  | Development
T04 | Frontend Core | 3 | 20 |  |  |  | Development
T05 | API Integration | 6 | 15 |  |  |  | Development
T06 | DB Schema | 2 | 5 |  |  |  | Development
T07 | CI/CD Pipeline | 7 | 6 |  |  |  | Infrastructure
T08 | Unit Tests | 5 | 12 |  |  |  | Testing
T09 | Integration Tests | 5 | 8 |  |  |  | Testing
T10 | Performance Testing | 5 | 5 |  |  |  | Testing
T11 | Code Review | 1 | 10 |  |  |  | QA
T12 | Security Audit | 7 | 4 |  |  |  | QA
T13 | Documentation | 8 | 5 |  |  |  | Delivery
T14 | Deployment | 7 | 3 |  |  |  | Delivery
T15 | Training | 8 | 4 |  |  |  | Delivery
Totals

## Budget
Project Budget Summary
Phase | Labor Cost | Contingency (15%) | Phase Total
Planning
Development
Infrastructure
Testing
QA
Delivery
Subtotal Labor
Management Overhead (10%)
Tools & Licenses | 3500
Total Project Cost
Cost per FTE
Cost per Task Day
Avg Task Cost

## Report
Executive Report
Total Budget
Labor Component
Labor %
Contingency
Overhead
Team FTE
Task Days
Effective Days
Efficiency
Largest Phase
Largest Phase Cost
Largest Phase Share
Risk Level
Budget Grade